## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PRJ_Airline_Reservation_01
Project Name | Airline Reservation System
Prepared/Modified by | Role | Date of Preparation
B,Sabareeshwari | Tester | 2018-07-15
Reviewed by | Role | Date of Review
SME
Approved by | Role | Date of Approval
Test Manager
Circulation List
Version Number | 1

## DEFECT TRACKING SHEET
Project ID: PRJ_Registration001 |  | Project Name : Registration
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_FLIGHT_001 | AUTHORITY LOGIN | The User name field in the page is found to accept characters less than 4 | Detailed Description: The User name field in the page is found to accept characters less than 4 Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Authority login 4. Enter Invalid Username(less than 4 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the any data in the Username field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_UserName_02 | [5 empty] | drg
DF_FLIGHT_002 | AUTHORITY LOGIN | The User name field in the page is found to accept characters more than 8 | Detailed Description: The User name field in the page is found to accept characters more than 8 Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Authority login 4. Enter Invalid Username(more than 8 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the any data in the Username field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_UserName_03
DF_FLIGHT_003 | AUTHORITY LOGIN | The password field in the page is found to accept characters less than 3 | Detailed Description: The password field in the page is found to accept characters less than 3 Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Authority login 4. Enter Invalid password(less than 3 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the any data in the password field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_Pwd_02
DF_FLIGHT_004 | AUTHORITY LOGIN | The password field in the page is found to accept characters more than 8 | Detailed Description: The password field in the page is found to accept characters more than 8 Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Authority login 4. Enter Invalid password(more than 8 characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the any data in the password field. The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2016-12-11 | Aman |  |  | Test Cycle 1 | TC_Pwd_03
DF_FLIGHT_005 | FLIGHT BASED ON PERIOD | The From date field in the flight details page is found older than current date. | Detailed Description: The From date field in the flight details page is found older than current date also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid From date 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the older date in the From field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | high | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_From_02 | [5 empty] | drg
DF_FLIGHT_006 | FLIGHT BASED ON PERIOD | The To date field in the flight details page is found older than From date. | Detailed Description: The To date field in the flight details page is found older than From date also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid From date 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the older date in the To field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_To_02 | [5 empty] | drg
DF_FLIGHT_007 | FLIGHT BASED ON PLACE | The source field in the flight details is found to accept same place as given in destination | Detailed Description: The source field in the flight details is found to accept same place as given in destination also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid source 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid source.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_Source_02 | [5 empty] | drg
DF_FLIGHT_008 | FLIGHT BASED ON PLACE | The destinatoin field in the flight details is found to accept same place as given in source | Detailed Description: The destination field in the flight details is found to accept same place as given in source also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid source 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid destinatoin.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_Destination_02 | [5 empty] | drg
DF_FLIGHT_009 | FLIGHT BOOKING | The user name field in the flight details page is found to accepts invalid name. | Detailed Description: The user name field in the flight details page is found to accepts invalid name also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid name 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid name.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_NoPersons_02 | [5 empty] | drg
DF_FLIGHT_010 | FLIGHT BOOKING | The email field in the flight details page is found to accepts invalid email. | Detailed Description: The email field in the flight details page is found to accepts invalid email also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid email 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid email.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Medium | Medium | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_EmailID_02 | [5 empty] | drg
DF_FLIGHT_011 | PAYMENT | The card details field is found to accept invalid alpha numerics values | Detailed Description: The card details field is found to accept invalid alpha numerics values also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid card details 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the invalid card details.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_card_02 | [5 empty] | drg
DF_FLIGHT_012 | PAYMENT | The card details field is found to accept more than 10 numbers | Detailed Description: The card details field is found to accept more than 10 numbers also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid card details 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts more than 10 numbers in card details field.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_card_03 | [5 empty] | drg
DF_FLIGHT_013 | BOOK FLIGHT | The name given in the from field is same as the to field | Detailed Description: The name given in the from field is same as the to field also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid To 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts invalid place.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_BTo_02 | [5 empty] | drg
DF_FLIGHT_014 | BOOK FLIGHT | The Departure date field is found to accept date less than the current date | Detailed Description: The depature date field is found to accept date less than the current date also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid Departure date 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts date less than the current date.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_Dept_02
DF_FLIGHT_015 | BOOK FLIGHT | The Number of travellers field found to accept invalid numbers | Detailed Description: The Number of travellers field found to accept invalid numbersalso Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid number of travellers 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts invalid number in the Number of travellers.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_NoTravellers_02
DF_FLIGHT_016 | PAYMENT | During payment, after giving card details and clicking make payment button, internal server error is shown. | Detailed Description: During payment, after giving card details and clicking make payment button, internal server error is shown. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on View Flights 4. Click on Book 5. Enter number of passengers. 6. Select class and click on submit. 7. By entering valid name and emailid click on Make Reservation button. 8. Enter the type of payment and enter the valid details and click on Make Payment button. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid payment details and proceed to payment but it is showing Internal Server Error. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_TOP_01
DF_FLIGHT_017 | EXECUTIVE | In book flight module, after selecting flight based on place it is not showing any error message when there is no available flights | Detailed Description: In book flight module, after selecting flight based on place it is not showing any error message when there is no available flights Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Book Flight 4. Enter valid details and click on search. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application should display list of flights available in order to book the flight. After selecting flight based on place it is not showing any error message when there is no available flights . | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_Source_01
DF_FLIGHT_018 | EXECUTIVE | When the user login as Executive, they should be able to view the flight occupancy details. | Detailed Description: When the user login as Executive, they should be able to view the flight occupancy details. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Login as Executive Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application should be able to allow the Executive to view the flight occupancy details | Coding | Google Chrome | Internal Dev | Low | Low | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_UserType_01
DF_FLIGHT_019 | EXECUTIVE | After login the user should be able to view the reservation details, update and cancel the booking. | "Detailed Description: After login the user should be able to view the reservation details, update and cancel the booking. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Login as User Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application should be able to allow the user to view the reservation details and update and delete the reservation details." | Coding | Google Chrome | Internal Dev | Low | Low | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_UserType_01
DF_FLIGHT_20 | LOGIN | Admin cannot be able to login into the website. | Detailed Description: Admin cannot be able to login into the website. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Admin 4. Enter valid username and password 5. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps though admin is clicked it is observed that it s not allowing. | Coding | Google Chrome | Internal Dev | High | High | 1.1 | Build 1.0 | 2016-12-11 | Aman |  | ACT | Test Cycle 1 | TC_UserType_02
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.